## Dashboard
Project Plant Pals: Operations & Training Plan
Description: This is a document resource overview for the Operations and Training plan for Office Green's new Plant Pals service.
Owner: Project Manager name
Status: Draft
Key Docs | Description
Project charter | An overview of the project, key elements and expectations
Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially.
Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle.
Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Folder with all relevant documentation
RACI chart | Identifies who is responsible, accountable, consulted and informed within the project.
Note on A7: Add hyperlink to digital document, Project charter
Note on A8: Add hyperlink to digital document, Statement of work
Note on A9: Add hyperlink to digital document, risk management plan
Note on A13: Add hyperlink to a shared folder
Note on A14: Add hyperlink to RACI chart spreadsheet

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: Project Manager | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Interview and hire delivery drivers | HR Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate delivery fees and estimate delivery schedule | Financial Analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Set up software systems for tracking inventory management and fulfillment | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Oversee the installation of fulfillment equipment | Inventory Manager | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Establish safety protocols and practices | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop a communication plan | HR Specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Develop the employee training program | HR Specialist | 5/17 | 5/28 | 20 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Train Office Green employees to use the software and equipment | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: Project Plant Pals Operations & Training | [6 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 64000 | $ - | 64000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks | -- |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials | -- |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | Delivery Drivers (2) | 160 | 15 |  |  |  | 2400 |  | -2400
[6 empty] | Total | 35400 | $ -
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source supplier (includes set up, installation and deployment of system) | -- |  |  |  |  | 15000 | 15000 |  | -15000
[6 empty] | Total | 15000 | $ -
Milestone 3: Develop and launch an employee training program
Task 1: Develop a communication plan for employees | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Develop a training program program | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 3: Train Office Green employees | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
[6 empty] | Total | 10000 | $ -
Reserve buffer | [6 empty] | 3600
TOTAL |  | 400 |  |  |  |  | 64000 | $ -

## Communication Plan
Project Plant Pals: Hiring Day Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Daily Stand-Up | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track
Facilities | Planning Meeting | Weekly | Core Team: Administrative Coordinator | Tuesdays at 2pm - 2nd, 9th, 16th | In Person | Reserve rooms/spaces
Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays - 4th, 11th, day before | Email (from individual address) | Coordinate printed materials/signage
Volunteers | Training | Weekly | Core Team: Administrative Coordinator | Email coordination Wed. 10th Training Wed. 17th | In Person | Coordinate with volunteers and send reminders
HR | Planning Meeting | Daily | Core Team: HR Specialist | Every day at 10am | Phone Call | Check in on planning progress, provide support to department
Your Manager | Project Update | Weekly | Project Manager | Monday afternoons | Email (from company address) | Update on event planning, ask questions, and get feedback
Candidates | Informational Update | Weekly | Core Team: HR Specialist | Email on the 5th, the 12th, and the day before the event | Email (from company address) | Communicate schedule, location, and other necessary event details
Volunteers | Training | One time | Core Team: Training Manager | The Wednesday before the event | In Person | Train volunteers to check-in and welcome candidates and direct the flow of traffic during the event
Catering | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays - 4th, 11th, day before | Email (from individual address) | Coordinate coffee service/snacks for candidates and lunch for HR
Senior Leaders: Director of Operations and the Director of Product (CC your manager) | Project Update | Weekly | Project Manager | Mondays - 8th, 15th, debrief after the event on the 19th | Email (from individual address) | High-level information and general updates