## Backlog
Order | Epic | User Story Title | Story | Acceptance Criteria | Value | Estimate | Sprint
1 | Plant Care Initiatives | Plant care kit | As a plant owner, I want to purchase a plant care kit so that I have the tools to tend to my plant. | 1. Design and source a plant care kit 2. Manufacture plant care kits 3. Include plant care kits with each purchase OR make them available as an add-on | $$ | 13 | Sprint_1
2 | Plant Care Initiatives | Customer chat | As a plant owner, I want a live customer chat so that I can ask a real person questions if my plant seems sick. | 1. Scope time commitment/resources for live chat 2. Install live chat operator on the website 3. Have experts from the team be available for live chat | $ | 13 | Sprint_1
3 | Bonsai Trees | Bonsai Trees: Browsing | As a customer, I want to browse for three different types of Bonsai Trees to purchase, so that I can get the exact tree I want. | 1. Source different Bonsai trees 2. Evaluate different "difficulty" levels of trees 3. Add content to the website around different levels of trees | $$ | 13 | Sprint_1
4 | Plant Care Initiatives | Low maintenance options | As a plant owner, I want to be able to select less high-maintenance plants, so that I can enjoy my plant for longer. | 1. Offer three different types of plants based on maintenance: Beginner, Intermediate, and Advanced 2. Source which plants would be the best offerings | $$$ | 8 | Sprint_1
5 | Plant Care Initiatives | Video tutorials | As a plant owner, I want to watch video tutorials so I can know how to better care for my plant. | 1. Write and produce a series of video tutorials 2. Design a release plan (posted on social media? linked in a customer email?) | $$ | 8 | Sprint_1
6 | Bonsai Trees | Bonsai Trees: Care and Maintenance Tools | As a customer, I want to purchase specific Bonsai tree care kits (including fertilizer, trimming shears, etc.), so that I can better care for my plant. | 1. Create various care packages 2. Add care package to online shop 3. Write product copy 4. Price accordingly | $$$ | 8 | Next Sprint
7 | Bonsai Trees | Bonsai Trees: Packaging and Delivery | As a customer, I want to receive my Bonsai tree in secure packaging, so that I know it'll get to me safely. | 1. Source appropriate packaging 2. Set up warehouse systems that use the packaging | $$$ | 8 | Next Sprint
8 | Plant Care Initiatives | Instruction manual | As a plant owner, I want to purchase an instruction manual so that I can get my plant to live for longer. | 1. Write and design an instructional manual 2. Produce hard copies to send with plants 3. Turn it into a page on the website | $$$ | 5 | Next Sprint
9 | Bonsai Trees | Bonsai Trees: Purchase Completion | As a customer, I want to complete the purchase of the Bonsai tree, so that I can have a tree shipped to me. | 1. Set up shopping cart, payment options, and purchase completion code on the website 2. Coordinate to show shipping tracking number | $$ | 5 | Next Sprint
10 | Bonsai Trees | Bonsai Trees: Care and Maintenance Booklet | As a customer, I want to access a Bonsai care booklet online and in hard copy, so that I can better care for my tree. | 1.Write and design a Bonsai tree care booklet 2. Coordinate distribution for the booklet | $$ | 5 | Next Sprint
11 | Plant Care Initiatives | Credit or return policy | As a plant owner, I want a credit or some kind of return policy so that I don't have to keep wasting money on dying plants. | 1. Discuss the viability of this (who's at fault?) 2. See if offering a credit is financially feasible | $ | 3 | Next Sprint
12 | Bonsai Trees | Bonsai Trees: Track Shipping | As a customer, I want to check on the shipping status of my order, so that I can see exactly when I'm going to get it. | 1. Enable shipping tracking in online portal 2. Set up automatic email when tracking number is available | $$$ | 3 | Next Sprint

## Sprints
Sprints | [5 empty] | Sprint Length in calendar days | 14 | Effort Values | 1
Name | Start date | End date | Points Capacity | Points Assigned | Value Attributed |  |  |  | 2
Sprint_1 | 2021-03-01 | 2021-03-14 | 60 | 55 | 10 |  |  |  | 3
Next Sprint | 2021-03-15 | 2021-03-28 | 60 | 37 | 17 |  |  |  | 5
8
13
21
Formulas:
End date = [Start date]+sprint_length-1
Start date = [Start date, row above]+sprint_length